## Team Members
Team Member | Contact Phone | Normal Hours | Normal Workdays
Catherine Warren | (206) 555-5555 | 8 | Mon - Fri

## Roles
Role | Team Member
Project Manager | Randal Root
Documentation Developer | Catherine Warren
Data Warehouse Developer | Catherine Warren
ETL developer | Catherine Warren
Cube Developer | Catherine Warren
Report Developer | Catherine Warren
Testers | Catherine Warren
Release Manager | Catherine Warren

## Solution Schedule
BI Solution Projects | Est Hours | Mon | Tue | Wed | Thur | Fri | Mon | Tue | Wed | Thur | Fri
Interview and Identify: | 28 | Mon: ***************************************
Planning and Documenting: | 18 | Thur: **************************
Create the Data Warehouse | 3 | Mon: ****
Extract, Transform, and Load: | 6 | Mon: **********
Create Cubes: | 6 | Mon: ********
Create Reports: | 6 | Mon: ********
Test the Solution: | 21 | Mon: **; Tue: *************************
Approve, Release, and Prepare for next version: | 9 | Thur: *****************

## Estimated Hours
BI Solution Projects | Task | Action Item | Estimated Hours | Actual Hours
Interview and Identify: | Interviews | Talk To Business Owner | 3
|  | Talk to Mangers | 3
|  | Talk to Users | 3
|  | Talk to DBA | 3
| Document Requirements | Create an informal overview | 3
|  | Create a BI solution worksheet | 3
| Locate Data | Review database tables | 3
|  | Review invoice documents | 3
|  | Review sales awards program | 3
| Discuss Feasibility | Decide if the solution will work | 1
28
Planning and Documenting: | Define Team Roles | What role fit this solution? | 1
| Define Team Members | Who will fill each role? | 1
| Define Team Schedule | When will we need them? | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Define IT requirements | Decide which Server will we use for DW, SSIS, SSAS, SSRS | 1
|  | Verify a time slot of Solution automation jobs | 1
| Define Security requirements | Decide which groups will have access to what? | 1
| Define Licensing requirements | Verify that the company has sufficient licensing | 3
| Estimate the cost | Hours * Wages + and additional 10% for unknowns | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Create formal documents | Complete BI solution worksheet | 3
|  | Create a Development Document | 3
18
Create the Data Warehouse | Create the Database | Create the Tables | 2
|  | Define Constraints | 1
3
Extract, Transform, and Load: | Create ETL Code | Create a SQL Script with ETL code | 3
|  | Create a an SSIS package with ETL code | 3
6
Create Cubes: | Create SSAS Database | Create Dimensions | 3
|  | Create Cubes | 3
6
Create Reports: | Create Prototype Reports | Create SSRS Reports | 3
|  | Create Excel Reports | 3
6
Test the Solution: | Requirements | Verify naming | 3
|  | Verify data domains | 3
|  | Verify formula results | 3
|  | Verify presentation formatting | 3
| Performance | Test SSIS ETL performance | 3
|  | Test SSAS Processing performance | 3
|  | Test SSRS Report performance | 3
21
Approve, Release, and Prepare for next version: | Finalize formal documents | Finish development document | 3
|  | Create a formal overview document | 3
|  | Create a lessons learned document | 3
9
|  | TOTAL | 106.7

## Data Warehouse
Data Warehouse Objects Worksheet
Object Name | Description | Source | Source Type | Source Nullable? | Destination Type | Destination Nullable?
DW-AdventureWorks-CWarren | Data Warehouse | AW_Project01_OLTP_DB | Database |  | Database
DW-AdventureWorks-CWarren.dbo.FactSales | Fact Table | AW_Project01_OLTP_DB.dbo.SalesOrderHeader | Table |  | Table
FactSales.OrderKey | Dimension Key Column | n/a | n/a | n/a | int | NO
FactSales.OrderID | Dimension Key Column | AW_Project01_OLTP_DB.dbo.SalesOrderHeader.SalesOrderID | int | NO | int | NO
FactSales.OrderDateKey | Dimension Key Column | n/a | n/a | n/a | int | NO
n/a | n/a | AW_Project01_OLTP_DB.dbo.SalesOrderHeader.OrderDate | datetime | NO | n/a | n/a
FactSales.CustomerKey | Dimension Key Column | n/a | n/a | n/a | int | NO
FactSales.CustomerID | Dimension Key Column | AW_Project01_OLTP_DB.dbo.SalesOrderHeader.CustomerID | int | NO | int | NO
DW-AdventureWorks-CWarren.dbo.FactSales (merged) | Fact Table | AW_Project01_OLTP_DB.dbo.SalesOrderDetail | Table |  | Table
(duplicate) | (duplicate) | AW_Project01_OLTP_DB.dbo.SalesOrderDetail.SalesOrderID | int | NO | n/a | n/a
FactSales.OrderDetailID | Dimension Key Column | AW_Project01_OLTP_DB.dbo.SalesOrderDetail.SalesOrderDetailID | int | NO | n/a | n/a
FactSales.ProductKey | Dimension Key Column | n/a | n/a | n/a | int | NO
FactSales.ProductID | Dimension Column | AW_Project01_OLTP_DB.dbo.SalesOrderDetail.ProductID | int | NO | n/a | NO
FactSales.OrderQty | Measure Column | AW_Project01_OLTP_DB.dbo.SalesOrderDetail.OrderQty | smallint | NO | int | NO
FactSales.UnitPrice | Measure Column | AW_Project01_OLTP_DB.dbo.SalesOrderDetail.UnitPrice | money | NO | money | NO
n/a | n/a | AW_Project01_OLTP_DB.dbo.SalesOrderDetail.UnitPriceDiscount | money | NO | money | n/a
DW-AdventureWorks-CWarren.dbo.DimProducts | Dimension Table | AW_Project01_OLTP_DB.dbo.Products | Table |  | Table
DimProducts.ProductKey | Dimension Key Column | n/a | n/a | n/a | int | NO
DimProducts.ProductID | Dimension Column | AW_Project01_OLTP_DB.dbo.Products.ProductID | int | NO | int | NO
DimProducts.ProductName | Dimension Column | AW_Project01_OLTP_DB.dbo.Products.Name | nvarchar(50) | NO | nVarchar(100) | NO
n/a | n/a | AW_Project01_OLTP_DB.dbo.Products.ListPrice | money | NO | n/a | n/a
DimProducts.ProductSubcategoryID | Dimension Column | AW_Project01_OLTP_DB.dbo.Products.ProductSubcategoryID | int | YES | int | YES
DW-AdventureWorks-CWarren.dbo.DimProducts (merged) | Dimension Table | AW_Project01_OLTP_DB.dbo.ProductSubcategory | Table |  | Table
(duplicate) | (duplicate) | AW_Project01_OLTP_DB.dbo.ProductSubcategory.ProductSubcategoryID | int | NO | n/a | n/a
DimProducts.ProductSubcategoryName | Dimension Column | AW_Project01_OLTP_DB.dbo.ProductSubcategory.Name | nvarchar(50) | NO | nvarchar(50) | YES
DimProducts.ProductCategoryID | Dimension Column | AW_Project01_OLTP_DB.dbo.ProductSubcategory.ProductCategoryID | int | NO | n/a | NO
DW-AdventureWorks-CWarren.dbo.DimProducts (merged) | Dimension Table | AW_Project01_OLTP_DB.dbo.ProductCategory | Table |  | Table
(duplicate) | (duplicate) | AW_Project01_OLTP_DB.dbo.ProductCategory.ProductCategoryID | int | NO | n/a | n/a
DimProducts.ProductCategoryName | Dimension Column | AW_Project01_OLTP_DB.dbo.ProductCategory.Name | nvarchar(50) | NO | nvarchar(50) | NO
DimProducts.StartDate | SCD Column | n/a | n/a | n/a | int | NO
DimProducts.EndDate | SCD Column | n/a | n/a | n/a | int | YES
DimProducts.IsCurrent | SCD Column | n/a | n/a | n/a | Char(3) | NO
DW-AdventureWorks-CWarren.dbo.DimCustomers | Dimension Table | AW_Project01_OLTP_DB.dbo.Customer | Table |  | Table
DimCustomers.CustomerKey | Dimension Key Column | n/a | n/a | n/a | int | NO
DimCustomers.CustomerID | Dimension Column | AW_Project01_OLTP_DB.dbo.Customer.CustomerID | int | NO | int | NO
DimCustomers.CustomerPersonID | Dimension Column | AW_Project01_OLTP_DB.dbo.Customer.PersonID | int | YES | int | NO
DimCustomers.CustomerAccountNumber | n/a | AW_Project01_OLTP_DB.dbo.Customer.AccountNumber | varchar(10) | NO | n/a | n/a
DW-AdventureWorks-CWarren.dbo.DimCustomerAccounts (merged) | Dimension Table | AW_Project01_OLTP_DB.dbo.Person | Table |  | Table
n/a | n/a | AW_Project01_OLTP_DB.dbo.Person.BusinessEntityID | int | NO | n/a | n/a
DimCustomers.CustomerName (firstname + lastname) | Dimension Column | AW_Project01_OLTP_DB.dbo.Person.FirstName | nvarchar(50) | NO | nVarchar(100) | YES
n/a (merged into CustomerName) | Dimension Column | AW_Project01_OLTP_DB.dbo.Person.LastName | nvarchar(50) | NO | nVarchar(100) | NO
DimCustomers.StartDate | SCD Column | n/a | n/a | n/a | int | NO
DimCustomers.EndDate | SCD Column | n/a | n/a | n/a | int | YES
DimCustomers.IsCurrent | SCD Column | n/a | n/a | n/a | Char(3) | NO
DW-AdventureWorks-CWarren.dbo.FactCustomerAddresses | Bridge Table (Factless Fact) | AW_Project01_OLTP_DB.dbo.PersonAddress | Table |  | Table
FactCustomerAddresses.CustomerAddressFactKey | Dimension Key Column | (generated) | n/a | n/a | int | NO
FactCustomerAddresses.CustomerKey | Dimension Column | n/a | n/a | n/a | int | NO
n/a | n/a | AW_Project01_OLTP_DB.dbo.PersonAddress.BusinessEntityID | int | NO | n/a | n/a
FactCustomerAddresses.AddressKey | Dimension Key Column | n/a | n/a | n/a | int | NO
n/a | n/a | AW_Project01_OLTP_DB.dbo.PersonAddress.AddressID | int | NO | n/a | n/a
FactCustomerAddresses.AddressTypeKey | Dimension Key Column | n/a | n/a | n/a | int | NO
n/a | n/a | AW_Project01_OLTP_DB.dbo.PersonAddress.AddressTypeID | int | NO | int | NO
FactCustomerAddresses.StartDate | SCD Column | n/a | n/a | n/a | int | NO
FactCustomerAddresses.EndDate | SCD Column | n/a | n/a | n/a | int | YES
FactCustomerAddresses.IsCurrent | SCD Column | n/a | n/a | n/a | Char(3) | NO
DW-AdventureWorks-CWarren.dbo.DimAddressTypes | Dimension Table | AW_Project01_OLTP_DB.dbo.AddressType | Table |  | Table
DimAddressTypes.AddressTypeKey | Dimension Key Column | n/a | n/a | n/a | int | NO
DimAddressTypes.AddressTypeID | Dimension Column | AW_Project01_OLTP_DB.dbo.AddressType.AddressTypeID | int | NO | int | NO
DimAddressTypes.AddressTypeName | Dimension Column | AW_Project01_OLTP_DB.dbo.AddressType.Name | nvarchar(50) | NO | nVarchar(100) | NO
DimAddressTypes.StartDate | SCD Column | n/a | n/a | n/a | int | NO
DimAddressTypes.EndDate | SCD Column | n/a | n/a | n/a | int | YES
DimAddressTypes.IsCurrent | SCD Column | n/a | n/a | n/a | Char(3) | NO
DW-AdventureWorks-CWarren.dbo.DimAddresses | Dimension Table | AW_Project01_OLTP_DB.dbo.Address | Table |  | Table
DimAddresses.AddressKey | Dimension Key Column | (generated) | n/a | n/a | int | NO
DimAddresses.AddressID | Dimension Column | AW_Project01_OLTP_DB.dbo.Address.AddressID | int | NO | int | NO
n/a | n/a | AW_Project01_OLTP_DB.dbo.Address.AddressLine1 | nvarchar(60) | NO | n/a | n/a
n/a | n/a | AW_Project01_OLTP_DB.dbo.Address.AddressLine2 | nvarchar(60) | YES | n/a | n/a
DimAddresses.AddressCity | Dimension Column | AW_Project01_OLTP_DB.dbo.Address.City | nvarchar(30) | NO | nVarchar(100) | NO
DimAddresses.AddressStateProvinceID | Dimension Column | AW_Project01_OLTP_DB.dbo.Address.StateProvinceID | int | NO | int | NO
DimAddresses.AddressPostalCode | Dimension Column | AW_Project01_OLTP_DB.dbo.Address.PostalCode | nvarchar(15) | NO | nVarchar(50) | NO
DW-AdventureWorks-CWarren.dbo.DimAddresses (merged) | Dimension Table | AW_Project01_OLTP_DB.dbo.StateProvince | Table |  | Table
n/a | n/a | AW_Project01_OLTP_DB.dbo.StateProvince.StateProvinceID | int | n/a | n/a | NO
DimAddresses.AddressStateProvinceCode | Dimension Column | AW_Project01_OLTP_DB.dbo.StateProvince.StateProvinceCode | nchar(3) | NO | nVarchar(10) | NO
DimAddresses.AddressCountryRegionCode | Dimension Column | AW_Project01_OLTP_DB.dbo.StateProvince.CountryRegionCode | nvarchar(3) | NO | nVarchar(10) | NO
DimAddresses.AddressStateProvinceName | Dimension Column | AW_Project01_OLTP_DB.dbo.StateProvince.Name | nvarchar(50) | NO | nVarchar(100) | NO
DW-AdventureWorks-CWarren.dbo.DimAddresses (merged) | Dimension Table | AW_Project01_OLTP_DB.dbo.CountryRegion | Table |  | Table
(duplicate) | (duplicate) | AW_Project01_OLTP_DB.dbo.CountryRegion.CountryRegionCode | nvarchar(3) | NO | nVarchar(10) | n/a
DimAddresses.AddressCountryRegionName | Dimension Column | AW_Project01_OLTP_DB.dbo.CountryRegion.Name | nvarchar(50) | NO | nVarchar(100) | NO
DimAddresses.StartDate | SCD Column | n/a | n/a | n/a | int | NO
DimAddresses.EndDate | SCD Column | n/a | n/a | n/a | int | YES
DimAddresses.IsCurrent | SCD Column | n/a | n/a | n/a | Char(3) | NO
DW-AdventureWorks-CWarren.dbo.DimDates | Dimension Table | n/a | n/a |  | Table
DimDates.DateKey | Dimension Key Column | n/a | n/a | n/a | int | n/a
DimDates.PlainDate | Dimension Column | n/a | n/a | n/a | date | n/a
DimDates.USADateName | Dimension Column | n/a | n/a | n/a | nVarchar(100) | n/a
DimDates.MonthKey | Dimension Column | n/a | n/a | n/a | int | n/a
DimDates.MonthName | Dimension Column | n/a | n/a | n/a | nVarchar(100) | n/a
DimDates.QuarterKey | Dimension Column | n/a | n/a | n/a | int | n/a
DimDates.QuarterName | Dimension Column | n/a | n/a | n/a | nVarchar(100) | n/a
DimDates.YearKey | Dimension Column | n/a | n/a | n/a | int | n/a
DimDates.YearName | Dimension Column | n/a | n/a | n/a | nVarchar(100) | n/a